## Subsystem Tracker
House BUS - Subsystem Design Tracks
Integration-first: each track names its interfaces (I1-I12) back to the shared loop/bus. Seeded stubs live in the folders below.
# | Subsystem | Folder | Priority/Seq | Status | Depends on | Key interfaces | Loads | Mass | Design doc
1 | Electrical & Power Distribution | 03_Electrical_Battery_Solar | 1 (foundation) | Detailed v0.1 | none | I6, I11, feeds all | Source | Y | Electrical_Power_Distribution.design.md
2 | Thermal / HVAC Integration | 04_Thermal_HeatPump_Coolant_CHP | 1 (keystone) | Detailed v0.2 | Electrical | I1,I2,I3,I4,I7,I8,I9 | Y | Y | Thermal_HVAC_Integration.design.md
3 | Water Systems | 07_Interior_and_Habitability | 2 | Detailed v0.1 | Electrical, Thermal | I10 (+I3) | Y | Y | Water_Systems.design.md
4 | Controls & Software | 08_Controls_and_Software | 2 | Detailed v0.2 | Electrical, Thermal | I12, reads all | Y | Y | Controls_and_Software.design.md
5 | Lighting & 48V Internal | 03_Electrical_Battery_Solar | 3 (research) | Detailed v0.1 | Electrical | 48V rail (post-I11) | Y | - | Lighting_and_48V_Internal.design.md
6 | Structure / Chassis / Mass | 06_Donor_Vehicle_and_Chassis | 2 (parallel) | Detailed v0.1 | none | hosts all | - | Y | Structure_Chassis_Mass.design.md
7 | Safety & Egress | 07_Interior_and_Habitability | 2 | Detailed v0.1 | Elec, Thermal, Controls | I12 interlocks | - | - | Safety_and_Egress.design.md
8 | Compliance / Registration / Insurance | 00_Admin_Budget_Schedule | parallel | Deferred (TJ) | none | n/a | - | - | (not started - checklist later)
Sequence: Electrical + HVAC sizing first (set loads & the bus) -> Water + Controls -> 48V-internal research -> Structure & Safety in parallel. Compliance deferred per TJ.
Each stub follows Subsystem_Design_TEMPLATE.md: Purpose -> Interfaces -> Components -> Loads -> Mass -> Open questions -> Sourcing.